## User stories
| Pixogram Story | Sub-Task
1 | User | Add User
Update User
Delete User
Show All users
2 | Content | Add Content
Add Comment
Delete Content
Show Particular user's content
Add likes/dislikes
3 | Admin | Add User
View User
Delete User
4 | Followers | Add Follower
Un follow
5 | Login Validation | Register
Login

## Riya
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Users
1.1 | Add User
1.1.1 | Html Page | 3 | 3
1.1.2 | Component | 1 | 1
1.1.3 | Validations + Exception Handling | 1.5 | 1.5
1.2 | Delete User
1.2.1 | Html Page | 1 | 1
1.2.2 | Component | 1 | 1
1.2.3 | Validations + Exception Handling | 1.5 | 1.5
1.3 | Update User
1.3.1 | Html Page | 2 | 2
1.3.2 | Component | 1.5 | 1.5
1.3.3 | Validations + Exception Handling | 1.5 | 1.5
1.4 | Show All Users
1.4.1 | Html Page | 1 | 1
1.4.2 | Component | 1 | 1
1.4.3 | Validations + Exception Handling | 1.5 | 1.5
1.5 | Registration + Login
1.5.1 | Html Page | 2 | 2
1.5.2 | Component | 2 | 2
1.5.3 | Validation | 1 | 1
1.5.4 | Integration with backend | 1 | 1

## Salonee
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Followers
1.1 | Add Followers
1.1.1 | Html Page | 3 | 3
1.1.2 | Component | 1 | 1
1.1.3 | Validations + Exception Handling | 1.5 | 1.5
1.2 | Unfollow
1.2.1 | Html Page | 1 | 1
1.2.2 | Component | 1 | 1
1.2.3 | Validations + Exception Handling | 1.5 | 1.5
1.3 | Show All Followers
1.3.1 | Html Page | 1 | 1
1.3.2 | Component | 1 | 1
1.3.3 | Validations + Exception Handling | 1.5 | 1.5

## Prerona
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Comments
1.1 | Add Comment
1.1.1 | HTML Page | 3 | 3
1.1.2 | Component | 1 | 1
1.1.3 | Validations + Exception Handling | 2 | 2
1.2 | See Comments for a particular content
1.2.1 | HTML Page | 3 | 3
1.2.2 | Component | 1.5 | 1.5
1.2.3 | Validations + Exception Handling | 1.5 | 1.5
1.3 | Remove Comment
1.3.1 | HTML Page | 2 | 2
1.3.2 | Component | 1.5 | 1.5
1.3.3 | Validations + Exception Handling | 2 | 2

## Nidhi
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Content
1.1 | Add Content
1.1.1 | Html Page | 3 | 3
1.1.2 | Component | 1 | 1
1.1.3 | Validations + Exception Handling | 1.5 | 1.5
1.2 | Delete Content
1.2.1 | Html Page | 1 | 1
1.2.2 | Component | 1 | 1
1.2.3 | Validations + Exception Handling | 1.5 | 1.5
1.3 | Show All Contents
1.3.1 | Html Page | 1 | 1
1.3.2 | Component | 1 | 1
1.3.3 | Validations + Exception Handling | 1.5 | 1.5
1.4 | View Particular Content
1.4.1 | Html Page | 1 | 1
1.4.2 | Component | 1 | 1
1.4.3 | Validations + Exception Handling | 1.5 | 1.5